## RFB
| #days | #mos
| 117 | 3.8466 |  | (timeline assumes that your request is #1 in bidding queue with no other requests ahead of it)
DATE | DAYS | WHO | ACTION | DESCRIPTION
2018-01-01 | 0 | REQ | RECEIVE | RQS/RQM and FINALIZED SPEC (required to initiate formal bidding process)
2018-01-03 | 2 | BUYER | SUBMIT | SPEC CHANGES #1 (clarifications and changes to the specifications from Purchasing)
2018-01-05 | 2 | REQ | SUBMIT | SPEC CHANGES #2 (clarifications and changes to the specifications from Department)
2018-01-08 | 3 | REQ | BUILD | BUILD RFB PACKAGE
2018-01-09 | 1 | PUR | BUILD | eBid on Planet Bids
2018-01-11 | 2 | BUYER | CONTACT | BIDDERS (for info updates)
2018-01-13 | 2 | BUYER | PACKAGE | RFB FOR REVIEW
2018-01-16 | 3 | APA | REVIEW | RFB PACKAGE (for final changes)
2018-01-17 | 1 | BUYER | ISSUE | RFB (out for at least 4 weeks)
2018-01-31 | 14 | BOTH | ATTEND | JOB WALK (if necessary; typically, 2 weeks after RFB is released)
2018-02-07 | 7 | BOTH | RECEIVE | QUESTIONS (at least 7 days prior to RFB opening)
2018-02-08 | 1 | BOTH | RESPOND | ANSWERS
2018-02-09 | 1 | BUYER | ISSUE | ADDENDUM
2018-02-16 | 7 | BUYER | RECEIVE | RFB
2018-02-18 | 2 | BUYER | POST | RESULTS (typically, 2 days after bid opening)
2018-02-18 | 0 | BUYER | SEND | BID EVAL
2018-02-21 | 3 | REQ | RECEIVE | BID EVAL (if Agreement & Staff Report is NOT required, award can be made in ~7 days)
2018-02-24 | 3 | BUYER | DRAFT | AGREEMENT (initial draft to agreement by buyer for CAO)
2018-03-06 | 10 | CAO | DRAFT | AGREEMENT (typically, 10 days after request is submitted to CAO)
2018-03-08 | 2 | BUYER | REVIEW | AGREEMENT
2018-03-15 | 7 | BUYER | OBTAIN | AGREEMENT SIGNATURES (contractor)
2018-03-17 | 2 | BUYER | OBTAIN | AGREEMENT SIGNATURES (CAO)
| -24 | n/a |  | if agreement is NOT required, enter N/A in column C
2018-02-24 | 3 | BUYER | DRAFT | STAFF REPORT(add time for agreement delays and additional clarifications)
2018-02-24 | 0 | BUYER | SUBMIT | STAFF REPORT DRAFT (at least 4 weeks prior to Council Meeting)
2018-03-03 | 7 | APA | REVIEW | STAFF REPORT for CHANGES
2018-03-10 | 7 | PA | SUBMIT | STAFF REPORT FINAL
2018-03-12 | 2 | DPT HD | CONUR | STAFF REPORT (Dept Head's signature re: concurrence)
2018-03-12 | 0 | PA | SUBMIT | STAFF REPORT
2018-03-19 | 7 | CLRK | SUBMIT | STAFF REPORT (at least 1 week prior to Council Meeting)
2018-03-26 | 7 | CC | APPROVE | CITY COUNCIL (mathematical projection only; not actual date)
| 0 |  |  | if staff report is NOT required, enter N/A in column C
2018-03-29 | 3 | PUR | AWARD | MA/PO
(the start section may be eliminated if it is not required)
2018-04-28 | 30 | CON | START | CONTRACT BEGINS (normally, 1st of the next month or 30 days ARO after dept has received insurance, business license, performance bond, approved submittals, etc.)
|  | APA | = | ASSITANT PURCHASING AGENT
|  | BOTH | = | REQ & PUR
|  | CAO | = | CITY ATTORNEY'S OFFICE
|  | CC | = | CITY COUNCIL
|  | CLRK | = | CITY CLERK
|  | CON | = | CONTRACTOR
|  | DPT HD | = | DEPARTMENT HEAD
|  | PA | = | PURCHASING AGENT
|  | PUR | = | PURCHASING
|  | REQ | = | REQUESTOR
Formulas:
DATE = [DAYS]+[DATE, row above]
DATE = [DAYS]+[DAYS, row above]+A25

## RFP
| #days | #mos
| 189 | 6.2137 |  | (timeline assumes that your request is #1 in bidding queue with no other requests ahead of it)
DATE | DAYS | WHO | ACTION | DESCRIPTION
2018-01-01 | 0 | REQ | RECEIVE | RQS/RQM and FINALIZED SPEC (required to initiate formal bidding process)
2018-01-03 | 2 | BUYER | SUBMIT | SPEC CHANGES #1 (clarifications and changes to the specifications from Purchasing)
2018-01-05 | 2 | REQ | SUBMIT | SPEC CHANGES #2 (clarifications and changes to the specifications from Department)
2018-01-10 | 5 | REQ | BUILD | BUILD RFP PACKAGE
2018-01-11 | 1 | PUR | BUILD | eBid on Planet Bids
2018-01-13 | 2 | BUYER | CONTACT | BIDDERS (for info updates)
2018-01-15 | 2 | BUYER | PACKAGE | RFP FOR REVIEW
2018-01-18 | 3 | APA | REVIEW | RFP PACKAGE (for final changes)
2018-01-19 | 1 | BUYER | ISSUE | RFP (out typically 6 weeks)
2018-02-02 | 14 | BOTH | ATTEND | PRE-PROPOSAL CONFERENCE (if necessary; typically, 2 weeks after bid is released)
2018-02-16 | 14 | BOTH | RECEIVE | QUESTIONS (at least 7 days prior to bid opening)
2018-02-23 | 7 | BOTH | RESPOND | ANSWERS
2018-02-24 | 1 | BUYER | ISSUE | ADDENDUM
2018-03-03 | 7 | PROPOSERS | SUBMIT | PROPOSAL
2018-03-17 | 14 | Eval team | SCORE | READ AND SCORE ALL PROPOSALS (typically, 14 days after bid opening)
2018-03-18 | 1 | Eval team | MEET | REVIEW PROPOSALS AND SCORES AS A GROUP
2018-03-25 | 7 | Eval team | INTERVIEW | SHORT-LISTED PROPOSERS BASED ON COMPETITIVE RANGE OF SCORES
2018-03-26 | 1 | BUYER | SEND | BEST AND FINAL OFFERS (BAFO) REQUESTED
2018-03-29 | 3 | BUYER | RECEIVE | BAFOs RECEIVED FROM SHORT-LISTED PROPOSERS
2018-04-05 | 7 | Eval team | SCORE | FINAL SCORE AND CONSENSUS
2018-04-07 | 2 | BUYER | POST | RFP RESULTS
2018-04-07 | 0 | BUYER | SEND | BID EVAL
2018-04-10 | 3 | REQ | RECEIVE | BID EVAL (if Agreement & Staff Report is NOT required, award can be made in ~7 days)
2018-04-13 | 3 | BUYER | DRAFT | AGREEMENT (initial draft to agreement by buyer for CAO)
2018-04-23 | 10 | CAO | DRAFT | AGREEMENT (typically, 10 days after request is submitted to CAO)
2018-04-25 | 2 | BUYER | REVIEW | AGREEMENT
2018-05-02 | 7 | BUYER | OBTAIN | AGREEMENT SIGNATURES (contractor)
2018-05-04 | 2 | BUYER | OBTAIN | AGREEMENT SIGNATURES (CAO)
| 0 | na |  | if agreement is NOT required, enter N/A in column C
2018-05-07 | 3 | BUYER | DRAFT | STAFF REPORT(add time for agreement delays and additional clarifications)
2018-05-07 | 0 | BUYER | SUBMIT | STAFF REPORT DRAFT (at least 4 weeks prior to Council Meeting)
2018-05-14 | 7 | APA | REVIEW | STAFF REPORT for CHANGES
2018-05-21 | 7 | PA | SUBMIT | STAFF REPORT FINAL
2018-05-23 | 2 | DPT HD | CONUR | STAFF REPORT (Dept Head's signature re: concurrence)
2018-05-23 | 0 | PA | SUBMIT | STAFF REPORT
2018-05-30 | 7 | CLRK | SUBMIT | STAFF REPORT (at least 1 week prior to Council Meeting)
2018-06-06 | 7 | CC | APPROVE | CITY COUNCIL (mathematical projection only; not actual date)
| 0 |  |  | if staff report is NOT required, enter N/A in column C
2018-06-09 | 3 | PUR | AWARD | MA/PO
(the start section may be eliminated if it is not required)
2018-07-09 | 30 | CON | START | CONTRACT BEGINS (normally, 1st of the next month or 30 days ARO after dept has received insurance, business license, performance bond, approved submittals, etc.)
|  | APA | = | ASSITANT PURCHASING AGENT
|  | BOTH | = | REQ & PUR
|  | CAO | = | CITY ATTORNEY'S OFFICE
|  | CC | = | CITY COUNCIL
|  | CLRK | = | CITY CLERK
|  | CON | = | CONTRACTOR
|  | DPT HD | = | DEPARTMENT HEAD
|  | PA | = | PURCHASING AGENT
|  | PUR | = | PURCHASING
|  | REQ | = | REQUESTOR
Formulas:
DATE = [DAYS]+[DATE, row above]
DATE = [DAYS]+[DAYS, row above]+A31